## Sheet1
|  | ID | Story Title | Depends On | Points | Priority | As a/an [user type] | I want [functionality] | So that [value] | NFR | Definition of Done | Epic ID | Notes | Status
|  | S0 | Example |  | 1 | Medium | Professor | to create requirements | my students understand. | Understandability | When students grok! | 0 |  | Open
| this feels more like part of a story than the whole thing | P0 | Deal |  | 2 | High | Player | Be dealt a hand | I have cards |  | When the I have 5 cards | 0
|  | P1 | Play card |  | 5 | High | Player | Place a card | The game can progress |  | When card is out of hand | 0
|  | P2 | Draw card |  | 5 | High | Player | To draw a card | The game can progress |  | When card is in hand | 0
| this is not an action that the player initiates | P3 | Win/Lose |  | 2 | High | Player | To win or lose | The game can end |  | Game ends | 0
R5, R8 | you can do this as a guest. Work on the value to the user here | A1 | Create account |  | 3 | High | Player | to make an account | so I can play |  | when this account is made | 1
R8 | this motivation too needs work | A2 | Update account |  | 3 | Medium | Player | to update the account | to change information |  | the account is updated | 1
R8 | ditto | A3 | Delete account |  | 3 | Low | Player | to delete the account | I can remove an account |  | Account is gone | 1
R8 | A1-A4 are CRUD account and so get 8 points total at most | A4 | Check account |  | 2 | High | Player | To view account info / balance | I know how much currency I have |  | When info is visible to user | 1
R8, R8 | why so main points? | P5 | Play Tutorial |  | 13 | Low | Player | To learn the game | I can understand the game |  | The tutorial is over | 0
R5 | part of creating a room/game | H3 | Add Bots |  | 5 | Low | Host | to have bots to play with | I can fill a game | Difficulty settings, if possible | When there are bots in my game | 2
|  | P7 | Join Game |  | 8 | High | Player | to join a game | to play | Can't join without host permission | When I join a lobby | 0
|  | P6 | View Games |  | 5 | High | Player | view all joinable games | I can find the game I want to join |  | When the player sees the list of active games | 0
|  | P8 | Bet |  | 3 | Low | Player | Bet on outcome of game | I can get rich quick |  | When player can bet on outcome of game before it begins | 0
|  | P9 | Click Ad |  | 3 | Low | Player | To click on an Ad | I go to the link | Ad quantity should not be annoying | When user is taken to homepage of advertisement | 0
|  | P12 | Report |  | 3 | Low | Player | Report another account | Bad account is seen by admins |  | Report is sent | 0
|  | P10 | Send Message |  | 5 | Medium | Player | To message others | I can communicate with them | Outside of game | When user can DM other players outside of game | 0
|  | P11 | Read message |  | 5 | Medium | Player | Read my messages | I can see what players have DMed me | Outside of game | When user can view all messages sent to them | 0
R5 | part of game/room creation | H1 | Set Game Password |  | 2 | Medium | Host | to set password | the game is private |  | Password is set | 2
R4 | the app handles this? | H2 | Allow Player |  | 1 | Medium | Host | to allow a player into the game | let players in |  | Players join game | 2
|  | H0 | Create game |  | 13 | High | Host | to make a game | I can play the game |  | When a game is able to be made | 2
| !SR | M0 | Kick user |  | 3 | Medium | Admin/Host | to get rid of a player | keep a good environment/keep the game running |  | When player has been removed from game | 3
| !SR | M1 | Pull user |  | 5 | Low | Admin | move a player to a game | they can play when there is an issue |  | When player is pulled into a game | 3
| where did the term "report" come from? | M2 | Read Report |  | 3 | Low | Admin | Read a report | can check if an account is being bad |  | Report is read | 3
| !SR | M3 | Ban account |  | 1 | Medium | Admin | to ban an account | cheaters cant play |  | When account is banned | 3
|  | M4 | Change Password |  | 1 | Low | Admin | to reset users password | user can get into their account |  | when password is different | 3
R3 | enter as guest, login to account, and friends list missing