## Sheet1
ID | Story Title | Depends On | Points | Priority | As a/an [user type] | I want [functionality] | So that [value] | NFR | Definition of Done | Epic ID | Notes | Status
S0 | Example |  | 1 | Medium | Professor | to create requirements | my students understand. | Understandability | When students grok! |  |  | Open
P0 | Play card |  | 5 | High | Player | Place a card | The game can progress | none yet | When card is out of hand
P1 | Draw card |  | 5 | High | Player | To draw a card | The game can progress | none yet | When card is in hand
A0 | Log in to account |  | 2 | High | Guest | To log into my account | so that I can use my account | none yet | When the player can access their account
A1 | Create account |  | 2 | High | Guest | to make an account | so they can play | none yet | when this account is made
A2 | Update account Information |  | 2 | Medium | Player | to update the account | to change information | none yet | the account is updated
A3 | Delete account |  | 2 | Low | Player | to delete the account | I can remove an account | none yet | Account is gone
A4 | Check account Information |  | 2 | High | Player | To view account info / balance | I know how much currency I have | none yet | When info is visible to user
P2 | Play Tutorial |  | 8 | Low | Player | To learn the game | I can understand the game | none yet | The tutorial is over
P3 | Join Game |  | 8 | High | Player/Guest | to join a game | to play | Can't join without host permission | When I join a lobby
P4 | View Games |  | 5 | High | Player | view all joinable games | I can find the game I want to join | none yet | When the player sees the list of active games
P5 | Bet |  | 3 | Low | Player | Bet on outcome of game | I can get rich quick | none yet | When player can bet on outcome of game before it begins
P6 | Click Ad |  | 3 | Low | Player | To click on an Ad | I go to the link | Ad quantity should not be annoying | When user is taken to homepage of advertisement
P7 | Report |  | 3 | Low | Player | Report another account | Bad account is seen by admins | none yet | Report is sent
P8 | Send Message |  | 5 | Medium | Player | To message others | I can communicate with them | looks like email | When user can DM other players
P9 | Read message |  | 5 | Medium | Player | Read my messages | I can see what players have DMed me | looks like email | When user can view all messages sent to them
H0 | Create game |  | 13 | High | Host | to make a game | I can play the game | set password, add bots, allow players | When a game is able to be made
M0 | Read Player Report |  | 3 | Low | Admin | Read a report | can check if an account is being bad | none yet | Report is read
M1 | Change Password |  | 1 | Low | Admin | to reset users password | user can get into their account | none yet | when password is different