## Sheet1
ID | Story Title | Depends On | Points | Priority | As a/an [user type] | I want [functionality] | So that [value] | NFR | Definition of Done | Epic ID | Notes | Status
S0 | Example |  | 1 | Medium | Professor | to create requirements | my students understand. | Understandability | When students grok! | 0 |  | Open
S1 | Deal |  | 2 | High | Player | Be dealt a hand | I have cards |  | When the I have 5 cards
S2 | Play card |  | 5 | High | Player | Place a card | The game can progress |  | When card is out of hand
S3 | Draw card |  | 5 | High | Player | To draw a card | The game can progress |  | When card is in hand
S4 | Win/Lose |  | 2 | High | Player | To win or lose | The game can end |  | Game ends
S5 | Create account |  | 3 | High | Player | to make an account | so they can play |  | when this account is made
S6 | Update account |  | 3 | Medium | Player | to update the account | to change information |  | the account is updated
S7 | Delete account |  | 3 | Low | Player | to delete the account | I can remove an account |  | Account is gone
S8 | Check account |  | 2 | High | Player | To view account info / balance | I know how much currency I have |  | When info is visible to user
S9 | Play Tutorial |  | 13 | Low | Player | To learn the game | I can understand the game |  | The tutorial is over
S10 | Add Bots |  | 5 | Low | Player | to have bots to play with | I can fill a game |  | When there are bots in my game
S11 | Join Game |  | 8 | High | Player | to join a game | to play |  | When I join a lobby
S12 | View Games |  | 5 | High | Player | view all joinable games | I can find the game I want to join |  | When the player sees the list of active games
S13 | Bet |  | 3 | Low | Player | Bet on outcome of game | I can get rich quick |  | When player can bet on outcome of game before it begins
S14 | Ads |  | 3 | Low | Player | To click on an Ad | I go to the link |  | When user is taken to homepage of advertisement
S15 | Report |  | 3 | Low | Player | Report another account | Bad account is seen by admins |  | Report is sent
S16 | Send Message |  | 5 | Medium | Player | To message others | I can communicate with them |  | When user can DM other players outside of game
S17 | Read message |  | 5 | Medium | Player | Read my messages | I can see what players have DMed me |  | When user can view all messages sent to them
S18 | Set Game Password |  | 2 | Medium | Host | to set password | the game is private |  | Password is set
S19 | Allow Player |  | 1 | Medium | Host | to allow a player into the game | let players in |  | Players join game
S20 | Create game |  | 13 | High | Host | to make a game | I can play the game |  | When a game is able to be made
S21 | Kick user |  | 3 | Medium | Admin/Host of Lobby | to get rid of a player | keep a good environment/keep the game running |  | When player has been removed from game
S22 | Pull user |  | 5 | Low | Admin | move a player to a game | they can play when there is an issue |  | When player is pulled into a game
S23 | Read Report |  | 3 | Low | Admin | Read a report | can check if an account is being bad |  | Report is read
S24 | Ban account |  | 1 | Medium | Admin | to ban an account | cheaters cant play |  | When account is banned
S25 | Change Password |  | 1 | Low | Admin | to reset users password | user can get into their account |  | when password is different